TERM SHEET: BUILD TRANSFER AGREEMENT

This preliminary non-binding term sheet is not intended to set forth any binding obligations on any party. The proposed transaction is conditioned upon mutually agreeable negotiation and execution of one or more definitive agreements, the approval of such agreements by the respective board of directors of each party, and the satisfaction of closing conditions contained in such definitive agreements. This preliminary non-binding term sheet does not by itself create or imply any legal rights or obligations between the parties or any other person, including without limitation any obligation to engage in negotiations or discussions or any exclusivity period for such negotiations or discussions. This preliminary non-binding term sheet may not cover all essential terms and conditions of the proposed transaction. This preliminary non-binding term sheet does not constitute a binding contract and the parties do not intend to be legally bound unless and until definite agreements have been executed. Unless and until definitive agreements have been executed, either party is free to terminate further negotiations at any time.

| Buyer | Puget Sound Energy Inc. |
| --- | --- |
| Seller | [………………..] |
| Facility Name | [………………..] |
| Facility Location | [………………..] |
| Project Company | [………………..] |
| Planned Nameplate [Power] Capacity | [………] MWAC (Point of Interconnection limit) [………] MWAC (Planned Capacity) |
| [Storage only] Energy Storage Capacity | [………] MWh |
| Product | A fully-built and commissioned Generating Facility. |
| Management Services post-Closing | Construction and Project Management through Final Completion. Seller is fully responsible for causing the Generating Facility to achieve Substantial Completion and Final Acceptance |
| % of Membership Interests Purchased | 100%. If partial ownership contemplated, please explain. |
| Point of Delivery | [………………..] |
| Closing Date | At Mechanical Completion |
| Guaranteed Commercial Operation Date (GCOD) | [………………..] |
| Contract Price | [$……..] |
| Payment Structure | Seller makes all payments required for construction through Final Completion |
| Payment Schedule | Closing Date (Mechanical Completion) = [___]% Substantial Completion = [___]% - Punch List Holdback Final Completion = [___]% + Punch List Holdback |
| [Battery Storage Only] Operational Parameter | At minimum: 365 cycles per year, max 2 per day, partial cycles allowed 0 – 100% SOC, 30-70% Annual Average SOC Up to 100 banked cycles for use following Contract Year |
| Title; Risk of Loss; and Care, Custody, and Control | Seller to ensure EPC and Major Suppliers transfer titles to the Project Company free of all encumbrances. Seller to ensure EPC to hold risk of loss, and care, custody, and control, of work and all equipment. Developer to ensure EPC to pass these to the Project Company as of Substantial Completion. |
| Interconnection | Seller responsible for meeting all interconnection requirements of the Interconnection Agreement Counterparty. Seller responsible for putting into place all required metering, telemetry, communication systems and other technical requirements under the Interconnection Agreement. [If applicable] Seller responsible for all systems requirements under Interconnection Agreement to pseudo-tie to Customer’s balancing area. |
| Transmission | Seller responsible for arranging for all transmission services required up to the Delivery Point. |
| Firm Date Conditions and Full Notice to Proceed | In addition to other customary Firm Date Conditions, - [Major Generation Equipment Supply] finalized; - EPC Agreement (that is executed or execution ready); - LGIA (that is execution ready); - Receipt of all discretionary permits as outlined in final and un-appealable form and substance satisfactory to Buyer - Final Price mutually agreed by the Parties. - Reps and Warranties are true and correct in all material respects - No Material Adverse Changes - Agreement on Title Policy Full Notice to Proceed to be issued within five (5) Business Days following the later of (a) the execution of the EPC Contract and (b) the Firm Date. |
| Closing Conditions | In addition to other customary Closing Conditions, - [For projects using ITC] Project achieved Mechanical Completion, and not synchronized to the electrical transmission system - Receipt of all permits as outlined in final and un-appealable form and substance satisfactory to Buyer - Seller shall transfer to Buyer all transmission service rights from Project to the POD. - Reps and Warranties are true and correct in all material respects - No Material Adverse Changes - Agreement on Title Policy |
| Pre-COD Milestones and Delay Liquidated Damages | If either Guaranteed Mechanical Completion or Guaranteed COD is not met, Seller shall pay daily delay liquidated damages of $500 x Planned Nameplate Capacity (MWAC). Guaranteed Mechanical Completion and Guaranteed COD may be extended by up to 180 days due to Force Majeure or Interconnection Delays in aggregate. |
| Early Termination and Pre-COD Termination Payment | Among other customary default terms, failure to achieve Mechanical Completion or GCOD within 180 days are events of default, with PSE right to terminate Agreement and collect Pre-COD termination payment of $100,000 per MW of Planned Nameplate Capacity, plus any delay LDs paid or payable by Seller. |
| Contract Capacity and Liquidated Damages | Seller shall not be permitted to achieve Substantial Completion unless the Contract Capacity determined by a Performance Test equals or exceed 95% of Planned Nameplate Capacity. |
| Warranty Terms | To be discussed - Minimum two years EPC warranty - Minimum two years major equipment warranties - Buyer review of major equipment warranties (prior to procurement for equipment not yet procured) |
| Labor | Seller shall (i) satisfy the Prevailing Wage Requirements and Apprenticeship Requirements applicable to the Project and (ii) execute an engineering, procurement and construction (“EPC”) contract for the Project that Washington Administrative Code, Title 296, Chapter 140 (“WAC 296-140”), which requires that the EPC contractor utilize a Project Labor Agreement, Community Workforce Agreement or Collective Bargaining Agreement, as applicable, in a reasonable and customary form, for major construction activities associated with the construction of the Project, and (iii) satisfy the requirements of Washington House Bill 1589 (“HB 1589”) as related to the Project. |
| Assignment by Seller | Assignment allowable only with Buyer’s consent. |
| Credit Support | Seller to provide credit support in the form of a) a parental guarantee with investment grade credit rating or otherwise and b) credit support in the form of a letter of credit equal to (1) $ 200,000/MWAC of Planned Nameplate Capacity prior to Closing Date and (2) $100,000/MWAC of Planned Nameplate after Closing Date. Letter of credit support to be sized at a minimum to match pre-COD Termination Payment plus maximum daily delay liquidated damages. |
| Other Material Changes | Please describe any other material changes made to proposed standard contract. |