## Instructions
The PSE Monitoring-Based Commisssioning (MBCx) program takes commissioning to the next leve by using software to collect, analyze and report data to optimize builidng energy performance and efficiency.
PSE Monitoring-Based Cx Process:
1. Customer or Cx Professional to complete the following tabs and submit pdf copies to: commissioning@pse.com:
a. "Pre-Screen" tab
b. Cx Professional application
c. PSE project application form
2. PSE Energy Management Engineer (EME) will evaluate the documentation and current utility billing information to determine eligibility.
3. Kickoff meeting with PSE, the customer, and the Cx Professional to discuss program commitments, benefits, and performance/grant targets
4. Contract created between PSE and the customer OR contractor.
5. The Cx Professional performs an initial review of your building’s systems to identify and report both O&M and potential capital opportunities for evaluation and implementation.
6. The Cx Professional completes implementation work and provides documentation to PSE and the customer (MBCx Plan) along with quarterly (MIN) reporting on the MBCx process.
7. The PSE EME will confirm the project completion and prepare a payment request for the base grant amount. The performance period, 10-12 and 20-24 months, begins at this point.
8. Following the performance period, PSE EME will evaluate the annual energy savings and submit a payment request for the appropriate performance grant amount.
Program Incentive Structure
| PSE Gas (other Elec.) | PSE Electric (other gas) | All PSE (Gas & Elec. or Elec. only)
Base Incentive >> | $0.05/sq.ft. | $0.10/sq.ft. | $0.15/sq.ft.
Performance Incentive 1 >> | $0.80/therm | $0.05/kWh
(period of 10-12 months)
Performance Incentive 2 >> | $0.80/therm | $0.05/kWh
(period of 20-24 months)
MBCx Sheet Descriptions:
• Prescreen sheet is to be completed and submitted with application for preapproval.
• IncentiveEst can be used by any party to quantify savings and incentive levels.
• EEI_SummaryTable is used during the investigation phase of commissioning.
• Cx_Schedule should be provided by Cx Professional with Cx plan.
•The implementation cost and training tracking should be used through the Cx phase and provide to PSE for payment.
• Performance_Changes should be provided at the end of the performance period for payment.

## Pre-screen
Facility: | [6 empty] | Application Date:
Owner:
Senior Operations: | [6 empty] | Management:
Building Details
| Total Area: |  | 50000 | Space type: |  | Other |  | Annual Usage: | 1000000 |  | kWh
[9 empty] | 20000 |  | therms
| Occupied |  | Start (AM) |  | End (PM)
| Weekday: |  | 6 |  | 5
Weekend:
Other:
This document serves as an initial screening tool to determine whether the building(s) would be a good candidate for this program or other programs within the PSE energy efficiency portfolio. Please mark the statements below that apply and submit to your PSE representative with a PSE Application for consideration.
PSE Application
Minimum Qualifications: |  |  |  | FALSE |  | FALSE
| Building(s) use |  |  | PSE Gas |  | PSE Electric
PSE gas only customers must use gas for space heating (e.g.: uses a condensing boiler, ventilation or make-up air heated by gas, not just for tempering the supply air)
Building(s) collectively have ≥ 50,000 conditioned square footage OR use significantly more energy than a typical office building (e.g.: 24/7 facility, museum, medical facility, MOB).
No major upgrades anticipated that will change how the equipment is operated (e.g. replacing constant volume HVAC with VAV, replacing controls).
No plans for controls system replacement or major upgrades within the next 5 years.
Building is at least 75% occupied
Additional Considerations to Qualify:
Building(s) is ≥ 1.5 year old.
Building energy use is > average for typical building of this type. Be sure to consider whether high use is controllable (associated with HVAC) or not (may include server rooms, DHW, Laundry, or other process loads).
Building Energy Use Index:
| Current: |  |  | 108.24 | Total kBTU/sq.ft. |  | 20 | kWh/sq.ft. | 0.4 | Therms/sq.ft
| Avg. for similar buildings: |  |  | 57.9557 | Total kBTU/sq.ft. |  | 6.3892 | kWh/sq.ft. | 0.36156 | Therms/sq.ft
Building has had several changes in use, or several different tenants since it was constructed.
Building does NOT have some of the energy efficient control sequences listed below (mark missing features):
Duct static/discharge air temperature/HW/CW/CHW reset based on load
Staging of chiller or boilers based on unit efficiency
Deadband for room temp setpoints
Optimum start/stop
VFDs
Other?
Building has never been commissioned by a third party (new or existing).
[5 empty] | If it has, date of last commissioning (Cx): |  |  | Cx Agent:
Ventilation rate has never been checked and there are no indoor air problems.
Building has had a lot of comfort, other issues, and/or does not seem to work right.
HVAC/lighting controls are not regularly tested, only basic maintenance has been done (e.g. change filters/belts).
Main HVAC system is NOT single zone packaged RTUs with wall stats.
HVAC systems have a BAS or DDC system. Last upgrade:
HVAC systems are complex systems:
Central hot water (boiler plant)
Central chilled water (chiller plant)
Variable Air Volume (VAV)
Multi-zone RTU
Other?
Major Reasons to Proceed:
List other reasons this building(s) is a good candidate. Include HVAC/lighting/controls issues building has had, findings from walk-through:
Give basic description of facility: # of buildings/systems in project, general hours of operation, HVAC type, lighting controls type, use of building, are there a lot of computers used, % of space for server rooms.
List changes in use or equipment in the past year and expected for the next 5 years. Explain briefly how one would easily adjust for this change in a billing savings analysis:
Other PSE Program that would help customer save energy:
Other Comments/Notes:

## MBCx_Schedule
Facility: |  |  |  | Date:
Directions: Add in dates based on max requirements; add notes as needed, complete participant information, update with actual completion dates
TASKS | DATES OF COMPLETION |  |  | Suggested & Maximum Time Frames & Notes (*PSE Review Max 2 weeks after submittal)
| CX Provider | PSE Review* | Owner
1. Proposal |  |  |  | Prior to grant
a. Scope of Work (incl. cost)
b. Initial CX Plan
2. Install sub-metering if needed |  |  |  | Min 2 months prior to Investigation
3. MBCx Planning Phase |  |  |  | 3 months
a. Create/Update CFR
b. Create MAP
c. Create training plan
4. EMIS Configure Phase |  |  |  | 3 months
a. Define data configuration requirements
b. Calibrate sensors
c. Configure FDD
d. Implement anomaly tracking
5. Implementation Phase |  |  |  | Min 3 months (quarterly/iterative)
a. Identify issues and opportunities |  |  |  | All items a through d are discussed during the quarterly
b. Investigate and analze |  |  |  | meetings and tracked
c. Identify and implement actions
d. Verify improvements
6. Facility Guide |  |  |  | Max 1 month after first verification cycle
a. Updated MBCx plan
b. Reporting (TBD)
7. Formal Training |  |  |  | 0.5 months after Facility Guide
9. 1st & 2nd Year Performance Bonus |  |  |  | During 1st & 2nd year after Facility Guide completion and
a. Issues/anomalies log |  |  |  | prior to performance payments
b. Quarterly meeting/reporting
c. Implementation cost tracking
PARTICIPANTS
Role | Name & Title |  |  | Contact Info (phone & e-mail)
PSE Engineer
CX Professional Lead
CX Professional Other
Owner Lead
Owner Training Participants
Owner Training Participants
Owner Training Participants
Owner Training Participants

## IncentiveEst (optional)
Monitoring-Based Cx Incentive/Goals: Calculator - Ver 9/21 | [6 empty] | 2021-09-16 13:45
Project Name: | PSE Customer, Building Name - MBCx | [9 empty] | Project Cash Flow
Customer: | PSE Customer | [9 empty] | Years | Invested | Incentive | Energy Savings | SPB | x | y
Address: | 1234 | [9 empty] | Yr 0 | -22500 | 22500 | 8505.635 |  | 3.7078 | 0
| Renton, WA 98057 | [9 empty] | Yr 1 | -25000 | 10800.8 | 12207.6186 |  | 3.7078 | 1
Project Type | All PSE (gas/elec) | Date: | 2020-03-26 | [7 empty] | Yr 2 | -25000 | 25000 | 13082.341
Electric Rate: | Sch 26 - Primary | Gas Rate: | Sch 31 | [7 empty] | Yr 3 | 0 | 0 | 13082.341
Provider Cost: | 50000 | [9 empty] | Yr 4 | 0 | 0 | 13082.341
Implementation Cost: | 22500 | $0.15/sq.ft. | [8 empty] | Yr 5 | 0 | 0 | 13082.341
SF: | 150000
Utility Data and Investment Variables | [8 empty] | Years | Invested | Incentive | Energy Savings | Net Annual | PV Rate | PV Rate | Initial investment | IRR Calc MIN
Annual Therms: | 20000 | 0.13333 | th./sq.ft. /yr. | [5 empty] | Yr 0 | -22500 | 22500 | 8505.635 |  |  |  | 72500 | -14199.2
Annual kWhs: | 2700000 | 18 | kWh/sq.ft./yr. | [5 empty] | Yr 1 | -25000 | 10800.8 | 12207.6186 | -1991.5814 | -1810.5285 |  | Incentive | -1991.5814
Total Building Energy Use |  | 74.7493 | kBTU/sq.ft./yr. | [5 empty] | Yr 2 | -25000 | 25000 | 13082.341 | 13082.341 | 10811.8521 |  | 58300.8 | 13082.341
Prefered Discount Rate: |  | 10% | (NPV Calc.) | [5 empty] | Yr 3 |  |  | 13082.341 | 13082.341 | 9828.9564 |  |  | 13082.341
Incentive Estimates | [8 empty] | Yr 4 |  |  | 13082.341 | 13082.341 | 8935.4149 |  |  | 13082.341
| Onboarding | Year 1 | Year 2 | [5 empty] | Yr 5 |  |  | 13082.341 | 13082.341 | 8123.1045 |  |  | 13082.341
MBCx Incentive with < 6% Savings
Incentives | 22500 | N/A | N/A | [11 empty] | 35888.7994
MBCx Incentive Estimate
| 22500 | 10800.8 | 25000
Maximum MBCx Incentive
Incentives | 22500 | 25000 | 25000
INSTRUCTIONS: In order to determine the estimated savings and incentive for your project all yellow cells must be populated as needed. If there are any process loads within the building that are largerer than 1% of the annual energy use, they must be account for below in the section labeled "Calculate Major Process Loads".
Calculate Major Process Loads (Loads > 1%)
Process Load Type |  | Load kW or therm/hr. | Annual Hours | Annual Use | UOM | Description
Data Center |  |  |  | 0
Large DHW |  |  |  | 0
Refrigeration |  |  |  | 0
Other (describe) |  |  |  | 0
Performance Incentive Estimate Calculation
| Percent Savings | Therms(gross) | kWhs (gross) | kbtus | Base Incentive | Performance Incentive | Phase Incentive | Percent Incentive
Base Incentive | 5% | 1000 | 135000 | 560620 | 22500 |  | 22500 | 31.03%
1st Year Performance | 6.979% | 1001 | 200000 | 782500 |  | 10800.8 | 10800.8 | 24%
2nd Year Performance | 7.9% | 2000 | 201000 | 885812 |  | 11650 | 11650 | 16.07%
Baseline Energy Use |  |  | Economic Analysis
| Total Use (Actual) |  |  | Annual Cost Savings | Simple Payback (SPB) | Internal Rate of Return (IRR) | Accounting Rate of Return (ARR) | Net Present Value (NPV)*
Electric | 2700000 |  |  | 13553.348 | 2.7078 | 44.82% | 13.89% | 21689.5994
Gas | 20000
*Uses a discount rate of 7.8% for the energy savings and a 3% inflation in energy cost throughout the 5 year measure life beginning in year 2 (net 4.8% decrease).
Project Notes:
Initial Grant Calc. | PSE Internal Use Only - Allocation by Measure
Measure Description |  |  | Measure Cost | PSE Grant | Savings (net) | Load Type | TRC | Baseline Use
MBCx Base (elec) |  |  | 20667.5106 | 20667.5106 | 135000 | Misc. | -9.99 | 2700000
MBCx Year 1 Perfromance (elec) |  |  | 23586.9334 | 23586.9334 | 65000 | Misc. | -9.99 | 2700000
MBCx Year 2 Perfromance (elec) |  |  | 22339.3292 | 22339.3292 | 1000 | Misc. | -9.99 | 2700000
MBCx Base (gas) |  |  | 1832.4894 | 1832.4894 | 1000 | Heating | -9.99 | 20000
MBCx Year 1 Perfromance (gas) |  |  | 1413.0666 | 1413.0666 | 1 | Heating | -9.99 | 20000
MBCx Year 2 Perfromance (gas) |  |  | 2660.6708 | 2660.6708 | 999 | Heating | -9.99 | 20000
Totals |  |  | 72500 | 72500
\\Sestdpt1.puget.com\Sopscci\4-Energy Efficiency\BEM\_Grants\250- CI Retro\_Commissioning\01_Monitoring Based (MBCx)\00_Onboarding\[MBCx_Forms_PSE_3.4.2021.xlsx]IncentiveEst (optional)
Data Center
Large DHW
Refrigeration
Pool
Other (describe)
Initial Grant
Final True-up*
0
0
Note on H40: Jason Hyatt: AVE net cash inflow / Initial investment
Note on E51: Jason Hyatt: PSE grant is based on the $0.05/kWh and $0.80/therm incentive rate and the "gross" savings.
Note on F51: Jason Hyatt: "net" savings are recorded savings by PSE.

## EEI_SummaryTable
[13 empty] | INVESTIGATION |  | REPORT
| Date: | [11 empty] | Energy Rates $ | kWh: | 0.072469 | Schedule | Sch 25 (>20,000 kWh/mo)
[7 empty] | kWh Savings | kWh std. dev. | Therm Savings | Therm std. dev. |  |  |  | Therm: | 0.8186 | Schedule | Sch 31
| Facility: | [5 empty] | 73333.3333 | 5270.4628 | 550 | 16.6667
| CX Provider (individual/company): | [14 empty] | Schedule
Owner Max Required Implementation Cost: |  |  | required $/sqft | 0.15 |  |  |  |  | Facility Conditioned Sqft | 150000 | [5 empty] | Max Required Implementation Cost | 22500
IMPROVEMENT |  |  |  |  | ESTIMATED SAVINGS | [10 empty] | IMPLEMENTATION |  |  | VERIFIED?
[7 empty] | Electric Savings |  |  |  | Gas Savings | [9 empty] | Electric Stats |  |  |  | Gas Stats
EEI # | Description | Existing Condition (Pre) | Proposed Condition (Post) |  | SPB (yrs) | Calc. (y/n) | Pessimistic est. (kWhs) | Optimistic est. (kWhs) | Most Likely est. (kWhs) | Expected Value (kWhs) | Pessimistic est. (therms) | Optimistic est. (therms) | Most Likely est. (therms) | Expected Value (therms) | Cost Savings ($) | Cost ($) | Date Done | Y/N | Y/N | Date | kWh Savings | Std. Deviation (σ) | Variance (σ²) | Therm Savings | Std. Deviation (σ) | Variance (σ²)
[5 empty] | 0.32525 | N | 10000 | 20000 | 15000 | 15000 | 500 | 600 | 550 | 550 | 1537.265 | 500 |  | Y |  |  | 15000 | 1666.6667 | 2777777.7778 | 550 | 16.6667 | 277.7778
[6 empty] | N | 50000 | 80000 | 55000 | 58333.3333 |  |  |  | 0 | 4227.3583 |  |  | Y |  |  | 58333.3333 | 5000 | 25000000 | 0 | 0 | 0
[7 empty] | 20000 | 100000 | 90000 | 80000 |  |  |  | 0 | 5797.52 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
[10 empty] | 0 |  |  |  | 0 | 0 | [7 empty] | 0 |  |  | 0
SUMMARY |  |  |  |  | 0.043245 | [7 empty] | 550 | 550 | 11562.1433 | 500 |  |  |  |  | 73333.3333 |  | 27777777.7778 | 550 |  | 277.7778
SUPPORTING DATA FOR SPREADSHEET:
Drop Down Lists
| REPORT TYPE | PSE $/sqft requirement |  | PSE utilities
| INVESTIGATION | 0.15 |  | All PSE
| FINAL | 0.1 |  | PSE elec (other gas)
|  | 0.1 |  | PSE gas (other elec)
UPGRADES
Y
N
Note on E8: All PSE customer: $0.15/sqft PSE elec (gas other): $0.10/sqft PSE gas (elec other): $0.10/sqft SCL elec (no gas): $0.10/sq.ft. PSE and SCL: $0.15/sq.ft PSE only (Seattle): $0.05/sq.ft.

## Performance_Changes
Directions: Note changes that have a major impact on energy use but were not a result of the commissioning (Cx) process.
Facility: |  | Owner:
Date of This Report: |  | Person Completing Report:
Date of Start of Cx Process:
Date of Final Cx Report:
Date end of 1st year Performance :
1 | Date or Date Range:
Description of Change or Event (e.g. occupancy changes, new equipment or tenant loads, production schedule, occupied hours etc.)
Describe how the change or event affects energy use. Estimate energy use impact (kWh/year, Therms/yr)
2 | Date or Date Range:
Description of Change or Event (e.g. occupancy changes, new equipment or tenant loads, production schedule, occupied hours etc.)
Describe how the change or event affects energy use. Estimate energy use impact (kWh/year, Therms/yr)
3 | Date or Date Range:
Description of Change or Event (e.g. occupancy changes, new equipment or tenant loads, production schedule, occupied hours etc.)
Describe how the change or event affects energy use. Estimate energy use impact (kWh/year, Therms/yr)
4 | Date or Date Range:
Description of Change or Event (e.g. occupancy changes, new equipment or tenant loads, production schedule, occupied hours etc.)
Describe how the change or event affects energy use. Estimate energy use impact (kWh/year, Therms/yr)

## Hidden (hidden)
List for Program Grant Amounts | [8 empty] | Sch_Elec (10-01-17) | Rates_Elec (¢ / kWh) | Demand ($ / kW) |  |  |  | 2019 CBSA Data - Typical PSE Comparison
Customer Type | Implementation $/sf | CX provider $/sf | Assessment | gas | elec | elec savings | gas savings |  | Sch 25 (<20,000 kWh/mo) | 9.4196 | 7.52 | PSE | sched. | $ | PSE Electric EUI (kWh/SF) |  |  |  | PSE Gas EUI (therms)
All PSE (gas/elec) | 0.15 | 0.35 | 5000 | 1 | 1 | 5% | 5% |  | Sch 25 (>20,000 kWh/mo) | 7.2469 | 7.52 | SCL/PSE | SCL Rates |  | Type | Median | Q1 | Q3 | Type | Median | Q1 | Q3
All PSE (all elec) | 0.15 | 0.35 | 5000 | 0 | 1 | 5% | 0% |  | Sch 26 - Primary | 5.6941 | 10.935 | SCL | Small GS | 0.0973 | Assembly | 7.9287 | 2.4 | 16 | Assembly | 0.44444 | 0.19 | 0.43
PSE elec/other gas | 0.1 | 0.25 | 4000 | 0 | 1 | 5% | 0% |  | Sch 26 - Secondary | 5.8898 | 11.285 |  | Medium GS | 0.077513 | Grocery | 40.2307 | 41 | 73 | Grocery | 0.57326 | 0.42 | 0.61
PSE gas/other elec | 0.1 | 0.15 | 2000 | 1 | 0 | 0% | 10% |  | Sch 31 | 5.6633 | 10.94 |  | Large GS | 0.089286 | Lodging | 10.8867 | 11 | 14 | Lodging | 0.43015 | 0.27 | 0.48
[9 empty] | Sch 40-HV | 5.4413 | 4.02 |  | High Demand GS | 0.0809 | Office | 11.8439 | 7.8 | 18 | Office | 0.16486 | 0.13 | 0.34
[9 empty] | Sch 40-Primary | 5.5191 | 4.11 |  | PSE Rates |  | Other | 6.3892 | 4.8 | 22 | Other | 0.36156 | 0.42 | 0.83
|  |  | Therm | None |  |  |  |  | Sch 40-Secondary | 5.6638 | 4.2 |  | Sch 25 (<20,000 kWh/mo) | 0.094196 | Residential Care | 14.7362 | 11 | 24 | Residential Care | 0.41015 | 0.23 | 0.4
|  |  | kWh | Electric |  |  |  |  | Sch 43 | 6.5084 | 4.98 |  | Sch 25 (>20,000 kWh/mo) | 0.072469 | Food Service | 39.613 | 20 | 39 | Food Service | 2.4757 | 0.86 | 1.7
[9 empty] | Sch 46 | 6.0828 | 2.09 |  | Sch 26 - Primary | 0.056941 | Retail | 9.5914 | 4 | 14 | Retail | 0.29059 | 0.2 | 0.33
|  |  |  | Gas |  |  |  |  | Sch 49 | 6.1964 | 3.7 |  | Sch 26 - Secondary | 0.058898 | School | 7.392 | 6.7 | 10 | School | 0.22459 | 0.37 | 0.51
[9 empty] | Sch_NG (10-01-17) | Rates_NG ($ / therm) |  |  | Sch 31 | 0.056633 | Warehouse | 3.716 | 1.2 | 3.6 | Warehouse | 0.14154 | 0.054 | 0.21
[9 empty] | Sch 31 | 0.8186 |  |  | Sch 40-HV | 0.054413
| Electric Cost Effectiveness Standard 2014/2015 Cents per KWH |  |  |  |  | Gas Conservation Cost Effectiveness Standard, 2014/2015 |  |  | Sch 41 < 5,000 | 0.50559 |  |  | Sch 40-Primary | 0.055191
Measure | Electric Space Heating | Misc. | Summer Cooling |  | Measure | Space Heating (Retrofit) | Hot Water (DHW) | Process | Sch 41 > 5,000 | 0.47308 |  |  | Sch 40-Secondary | 0.056638
Life | 1 | 3 | 4 |  | Life | 1 | 2 |  | Sch 85 Interruptible <25k | 0.47736 |  |  | Sch 43 | 0.065084
5 | 56.0656 | 39.3879 | 31.9985 |  | 5 | 4.7147 | 4.0836 | 3.8424 | Sch 85 Interruptible 25-50k | 0.41962 |  |  | Sch 46 | 0.060828
[9 empty] | Sch 85 Interruptible >50k | 0.41682 |  |  | Sch 49 | 0.061964
Note: These costs include the conservation credit. |  |  |  |  | Note: These costs do not include a conservation credit. |  |  |  | Sch 86 Interruptible <1,000 | 0.62121
[9 empty] | Sch 86 Interruptible >1,000 | 0.55139
[9 empty] | Sch 87 Interruptible <25k | 0.52439
Sch 8 | 8.9485 |  | Sch_NG (11-01-13) | Rates_NG ($ / therm) |  |  |  |  | Sch 87 Interruptible 25-50k | 0.46048
Sch 11 (<20,000 kWh/mo) | 8.6618 |  | Sch 31 | 0.96898 |  |  |  |  | Sch 87 Interruptible 50-100k | 0.425
Sch 11 (>20,000 kWh/mo) | 6.4847 |  | Sch 41 < 5,000 | 0.67526 |  |  |  | Initial Grant Calc. | Sch 87 Interruptible 100-200k | 0.40271
Sch 12 - Primary | 5.0994 |  | Sch 41 > 5,000 | 0.64573 |  |  |  | Performance Calc. | Sch 87 Interruptible 200-500k | 0.39154
Sch 12 - Secondary | 5.2951 |  | Sch 85 Interruptible <25k | 0.66765 |  |  |  |  | Sch 87 Interruptible >500k | 0.38496
Sch 24 | 9.6279 |  | Sch 85 Interruptible 25-50k | 0.61191
Sch 25 (<20,000 kWh/mo) | 9.3412 |  | Sch 85 Interruptible >50k | 0.60889
Sch 25 (>20,000 kWh/mo) | 7.1641 |  | Sch 86 Interruptible <1,000 | 0.78773
Sch 26 - Primary | 5.7788 |  | Sch 86 Interruptible >1,000 | 0.72431 |  |  |  |  | SCL Rates
Sch 26 - Secondary | 5.9745 |  | Sch 87 Interruptible <25k | 0.70844 |  |  |  |  | Small GS | 0.0973
Sch 29 (<20,000 kWh/mo) | 7.6959 |  | Sch 87 Interruptible 25-50k | 0.64679 |  |  |  |  | Medium GS | 0.077513
Sch 29 (>20,000 kWh/mo) | 6.1523 |  | Sch 87 Interruptible 50-100k | 0.61254 |  |  |  |  | Large GS | 0.089286
Sch 31 | 5.7888 |  | Sch 87 Interruptible 100-200k | 0.59105 |  |  |  |  | High Demand GS | 0.0809
Sch 40-HV | 5.4413 |  | Sch 87 Interruptible 200-500k | 0.58027
Sch 40-Primary | 5.5191 |  | Sch 87 Interruptible >500k | #VALUE!
Sch 40-Secondary | 5.6638 | [7 empty] | Implementation Cost
Sch 43 | 6.508 | [7 empty] | 0.05
Sch 46 | 6.0489 | [7 empty] | 0.1
Sch 49 | 6.1026 | [7 empty] | 0.15
Y
N

## Training Tracking
Project Name/Facility:
Traininer(s)
Hands on Training OR Other O&M Staff Time
Date | Hours | Staff Name (First/Last) | Title | Activity/Topic | Training Met Needs (y/n)
Facility Guide Training
Date | Hours | Staff Name (First/Last) | Title | Activity/Topic | Training Met Needs (y/n)

## Implementation_Cost
Facility:
1. Only include eligible improvements items. Review guidelines for what is considered an eligible improvement item/expenses and only include items that are eligible
2. Track the cost of implementing the improvements
3. Attach appropriate invoices to match costs for each item list & note EEI # that this item is for.
4. Note if item was already in owner's/ O&M stock
NOTE: Up to pre-determined maximum cost is required
Maximum Required Cost: |  |  | 0 | Facility sqft: | 50000 | Required $/sqft:
EEI# | Cost ($) | Item in Stock | Description |  |  |  | Drop Down Lists
[7 empty] | UPGRADES | PSE $/sqft requirement | PSE utilities
[7 empty] | Y | 0.15 | All PSE
[7 empty] | N | 0.1 | PSE elec (other gas)
[8 empty] | 0.05 | PSE gas (other elec)
0.16
TOTAL | 0 | CUSTOMER IMPLEMENTATION COST